## Sheet1
Date | Description | Which Event | Key Responsibility | Reviewers | Comments
2024-10-07 | #ITEOrlando2025 Call for Abstracts Released | Annual Meeting | Matt J | Kathi, Bridget, Pam
Tuesday, December 3, 2024 | Deadline for #ITEOrlando2025 Call for Abstracts | Annual Meeting | Pam G | none | Thanksgiving is November 28. We traditionally set the deadline the Tuesday after Thanksgiving. This is an eight week period
2024-10-01 | #ITEOrlando2025 Call for Abstracts Finalized | Annual Meeting | Matt J | Matt H, Bridget, Pam
September 1-September 30, 2024 | Development of #ITEOrlando2025 Call for Abstracts | Annual Meeting | Matt J | Matt H, Bridget, Pam
September 1-September 30, 2024 | Development of Exhibitor and Sponsor Prospectus | Spring Conference and Annual Meeting | Pam and Darlene | Kathi, Colleen, Adam
2024-10-01 | Exhibit and Sponsor Sales Begin | Spring Conference and Annual Meeting | The Wyman Company
September 1-September 30, 2024 | Revise and Update Prospect List | Spring Conference and Annual Meeting | Steve, Matt H., Pam
August 15-30, 2024 | Discussion and Determination of Themes | Spring Conference and Annual Meeting | Steve, Kathi, Colleen, Matt H, Bridget, Matt J
2024-10-01 | #ITEOrlando2025 Website Goes Live | Annual Meeting | Pam G
2024-12-01 | Spring Conference Website Goes Live | Spring Conference | Pam G
2025-01-01 | 2024 Excellence in Transportation Awards Nominations Open | Annual Meeting | Bridget - Awards; Pam - marketing
2025-01-28 | Final Content for Spring Conference Due | Spring Conference | Tech staff |  | This is eight weeks before the Spring Conference
2025-01-15 | Production of Spring Conference insert for March Issue of ITEJ begins | Spring Conference | Pam | Steve, Kathi, Colleen, Adam, Bridget
2025-02-03 | Tours for Annual Meeting Finalized | Annual Meeting | LAC and Adam
2025-02-13 | Production on Spring Conference Guidebook starts | Spring Conference | Content - tech staff; Pam - development | Kathi, Adam, Bridget/Holly, Tech staff representative
February 20-March 4, 2024 | Spring Conference Session Recordings | Spring Conference | Tech staff/Adam/Stephen
2025-02-28 | Early Bird Deadline for Spring Conference (there will be an automatic extension through the weekend. The extension is not published.) | Spring Conference | Colleen |  | This is a little more than three weeks before the Spring Conference
2025-03-08 | Final Bios and Headshots Needed for Learning Hub Platform | Spring Conference | Kellyanne/Tech Staff
March 19-23, 2024 | Platform Training | Spring Conference | Tech Staff
2025-03-12 | Spring Conference Plenary Session Scripts Drafted | Spring Conference | Bridget
2025-03-06 | Learning Hub Launched | Spring Conference | Kellyanne
2025-03-17 | Spring Conference Plenary Session Scripts Finalized | Spring Conference | Bridget
2025-03-19 | Session Title Powerpoints Finalized | Spring Conference | Pam
2025-03-17 | Spring Conference Guidebook Finalized | Spring Conference | Pam
| Spring Conference Plenary Powerpoints Drafted | Spring Conference | Bridget
2025-03-19 | Spring Conference Guidebook Circulated to Attendees | Spring Conference | Pam
2025-03-20 | Spring Conference Plenary Powerpoints Finalized | Spring Conference | Bridget
2024-03-25 | Announcement of Jeff Lindley Award during Plenary and Press Release | Spring Conference | Steve/Bridget
March 25-26, 2024 | Spring Conference | Spring Conference
2025-03-14 | Deadline for Young Leader to Follow Applications/Nominations | Annual Meeting
2025-03-21 | Following information due for ITEJ May wrap; schedule of events, sponsors | Annual Meeting | Pam | Steve, Kathi, Colleen, Adam, Bridget
2025-04-04 | District Representatives submit candidates for District Rising Star; Submissions for District Innovation Awards, Section Momentum Award, Student Chapter Award due; Submissions for Council awards due from Councils | Annual Meeting
2025-04-10 | Additional Content for Annual Meeting website due. This includes schedule, session topics, tracks, tours, workshops, council and committee meetings | Annual Meeting | Kathi, Adam, tech staff |  | This is about 12 weeks before the Annual Meeting
2025-05-19 | Annual Meeting website and mobile app content uploaded. Note: in many cases, I use the links from the mobile app platform to populate the Annual Meeting website. This means information only needs to be updated in one place. | Annual Meeting | Pam | Kathi, Adam, Bridget/Holly, Tech staff representative
2025-04-15 | Selection Committee Evaluation and Selection Complete (Awards) | Annual Meeting
2025-04-22 | Production of ITEJ June Insert. Any information requested but not provide by earlier deadlines is due | Annual Meeting | Pam
TBD | Spring IBOD Meeting | Annual Meeting
TBD | Signage Requests due to Adam | Annual Meeting | All Staff | Kathi, Colleen, Pam | We are going to need to account for design time
2024-05-26 | Content for Spring Conference Expires Online/Deadline to Earn Credit | Spring Conference | Kellyanne/Pam
TBD | State of the Association Outline/Powerpoint Started | Annual Meeting | Steve/Bridget
| Promotion of Mobile App Begins | Annual Meeting | Pam
2025-06-13 | Proposed Early Bird Registration Deadline for Annual Meeting | Annual Meeting | Colleen |  | This is seven weeks before the start of the meeting
TBD | Signage Orders due to Fern | Annual Meeting | Adam
2024-07-07 | Production of AM Guidebook begins | Annual Meeting | Pam | Kathi, Adam, Bridget/Holly, Tech staff representative
TBD | Hotel Room cut-off | Annual Meeting | Adam
2024-06-28 | Scripts Drafted | Annual Meeting | Bridget
2025-07-28 | Scripts Finalized | Annual Meeting | Bridget
2025-07-22 | Draft Attendee Survey | Annual Meeting | Adam | Kathi, Pam, Steve
2025-07-28 | Session Title Powerpoints Finalized | Annual Meeting | Pam
TBD | All boxes to be shipped to the Meeting packed and labeled | Annual Meeting | Staff
TBD | Freight departs ITE for Meeting | Annual Meeting | Adam
2024-08-07 | Freight Arrives at Meeting | Annual Meeting | Adam
2024-08-12 | Award Press Releases Issues | Annual Meeting | Bridget
August 10-13, 2025 | Annual Meeting and Exhibition | Annual Meeting
2025-08-13 | Attendee Survey Goes Out | Annual Meeting | Pam/Stephen
| All boxes returning to ITE following meeting to be packed and labeled; Freight picked up from hotel | Annual Meeting | Staff/Adam
2025-08-14 | Post-Meeting Website Published | Annual Meeting | Pam/Stephen
2025-10-24 | Deadline to Access Content from the Annual Meeting and PDHs | Annual Meeting | Kellyanne